## Sheet1
BPC Cemetery Carols - Monday 23rd December (revised post event)
Item | Description | Detail / Who | Action Owner | Comment/Issues | Confirmed
Preparation
ü
1.01 | Publish date - Facebook |  |  | Event
1.02 | Publish date - BPC website |  |  | Event & Diary
1.03 | Publish date - Laminated Posters | Helen Pratt | Helen Pratt
1.04 | Book Pianist | Andy Walton | Helen Pratt | Agree which sheet to use
1.05 | Source electronic piano & delivery | Andy Walton |  | Connection to PA - advise
1.06 | Book Compere | Lindsay McNish | Helen Pratt
1.07 | Carol sheets - check & order more if needed (3 options) | Sheet 1 - need at least 175 sheets | Need to collect | Memorial Hall cupboard
1.08 | Organise Clean Chapel | Bucklebury Guide leaders | Vicky Pratt
1.09 | Generator & Lights - Confirm | Steve Beeson | 3 kVA
1.10 | PA - Confirm | David Southgate | External & chapel
1.11 | Mince pie production - request | Georgina, Barry, David, Graham P + others (tbc)
1.12 | Mulled wine production - confirm | Andrea Varney Agree a target max budget for the MW
1.13 | Purchase paper cups (how many: 200-300?) | Need to check in Chapel
1.14 | Purchase mulled wine ingredients (what?) | Andrea to get recipe from Sarah Beeson.
1.15 | Hot blackcurrant | Anne Hillerton | Insulated flasks from BPC coffee morning box
1.16 | Purchase tea lights (how many: 100 x 4 hours?) | Amazon | New each year - reuse of used ones is a false economy
1.17 | Request gas fire lighters to be brought by BPC members | To light tea lights
1.18 | Gazebo & delivery - confirm | Bucklebury Guides
1.19 | Tables for Gazebo & delivery - confirm | Stored in the Chapel, belong to Guides (please wipe off afterwards).
1.20 | Insulated Urn | Graham Plank | Jason Allum to request
1.21 | Should we have a first aider / first aid kit? | First Aid Kit in car
1.22 | Charity | Written summary of charity for compere
1.23 | Review Risk Assessment and Event Emergency Plan | Publish once complete to BPC | Check if notifications required
Set up (Afternoon of 23rd)
2.01 | Clean & decorate - Chapel | Barry, Jason & Anne | Holly / green stuff off common
2.02 | PAT test electrics | David Southgate
2.03 | Generator & Lights deployed | Steve Beeson
2.04 | PA deployed | David Southgate
2.05 | Christmas inflatables deployed (weather permitting) | Not if windy
2.06 | Piano set up in Chapel | Andy Walton
2.07 | Gazebo set up | David Southgate | If in any doubt about the weather set up.
2.08 | Tables set up | David Southgate
2.09 | Battery lights set up for gazebo | If needed otherwise use SBs lights
2.1 | Tea lights prepared
2.11 | Song sheets in chapel
2.12 | Note on chapel for very young and elderly / disabled
2.13 | Two buckets for charity collection delivered | Jason Allum
2.14 | Sum-up machines tested and ready | Graham Loader
2.15 | Two + rubbish sacks set up |  | Black bin bags
2.16 | Collect insulated urn and deliver to Goring House | Jason Allum
2.17 | Take cleaning cloths & floor brush to chapel | David Southgate
2.18 | If possible agree someone to take turns to stay at the chapel so equipment can be left set up in the day light.
Set up (Evening of 23rd)
3.01 | Lights, piano & inflatables on |  | Steve Beeson
3.02 | Tea lights lit |  | BPC Present
3.03 | Mince pies on table
3.04 | Mulled wine, cups & fruit juice on table (ladle?)
3.05 | PA adjust |  | David Southgate
3.06 | 2 BPC with song sheets and buckets at entrance |  | BPC Present | BPC in hi-vis to be visible regarding Martins Law
3.07 | Write list of people who need to be thanked to give to Lindsay McNish plus charity summary |  | Helen/David
3.08 | Floor mats down as surface can be slippery
3.09 | Rope off grave area to reduce tripping hazard on either side of entrance | Rope - Jason 12 Stakes - David Club Hammer - David
3.10 | Open big gates
The Event (Evening of 23rd)
4.01 | Safety brief to BPC & emergency response. BPC members to wear hi-vis to be obvious | Key incident responses to be shared | BPC Present
4.02 | 2 BPC with song sheets and buckets at entrance |  | BPC Present
4.03 | 3 BPC serve drinks & mince pies | Hilary & Anne?? | BPC Present
4.04 | Collect carol sheets at the end |  | BPC Present
4.04 | Thanks to attendees and those who set up |  | Compere
Post Event (Evening of 23rd & following morning)
5.01 | Tea lights out and stored in the chapel |  | BPC Present
5.02 | Gazebo & tables down and stored in the chapel/returned. Wipe down tables | If gazebo wet, please leave half up in Chapel to dry. | BPC Present
5.03 | Lights, piano, inflatables, generator off & returned |  | BPC Present & Steve Beeson
5.04 | Carol sheets stored
5.05 | Rinse out insulated urn and return to Graham Plank
5.06 | Chapel swept - floor mats back on benches |  | BPC Present
5.07 | Money to Helen for counting & banking
5.08 | All go home
5.09 | Check all clear next morning
5.10 | Dry out / sort carol sheets
5.11 | Publish funds raised on Website and Facebook
5.12 | Review and update this list for next year